## Лист1
Task ID: | Task Name | Story | Sprint Ready | Priority | Status | Story Points | Assigned to Sprint | Assigned to:
| Sprint 1 | Yes | No | High | Complete | 32 | No
TASK-01 | Implementing a certain feature | Yes | Yes | High | Complete | 8 | Yes | Daniela
TASK-02 | Writing Software Requirment Specification | Yes | Yes | High | Complete | 16 | Yes | Daniela
TASK-03 | Writing mock-ups | Yes | Yes | Medium | Complete | 8 | Yes | Kriz
| Sprint 2 | Yes | No | High | In Progress | 34 | Yes
TASK-04 | Writing Test plan | Yes | Yes | High | Complete | 10 | Yes | Kriz
TASK-05 | Writing Test scenarios with Test cases | Yes | Yes | High | In Progress | 16 | Yes | Krasimir/Katerina
TASK-06 | Writing Functional Specification | No | No | Medium | In Progress | 8 | Yes | Kriz
| Sprint 3 | No | No | Medium | In Progress |  | No
TASK-07 | Automated Tests | Yes | No | Medium | In Progress | 20 | Yes | Daniela/Kriz/Krasimir
TASK-08 |  | No | No | Low | Not Started |  | No
TASK-09 | Fixing bugs | No | No | Low | Not Started |  | No